## Infrastructure Around Private Assets: The Legal Landscape

### 1. Types of Work

This category includes:

- Site servicing (storm, sanitary, watermain connections)

- Road widening or access upgrades

- Utility relocations

- Stormwater ponds or retention systems

- Hydro, telecom, and lighting installations

- Sidewalks, curbs, paving tied to development charges

These are often required by:

- Site Plan Agreements

- Subdivision Agreements

- Development Charges Agreements

Even if the developer pays, the work is governed by public standards (e.g., OPSS specs, municipal approvals), and the owner must post security to ensure it’s completed properly.

### 2. Who Are the Players?

- Private developers or property owners

- Contractors and subs

- Municipal reviewers (engineering or infrastructure departments)

- Consulting engineers (often contract administrators)

- Sometimes utility companies (Enbridge, Hydro, Bell) also act as gatekeepers

### 3. Legal Risk Zones

Even though the job is “private,” a lot of public-sector headaches show up:

#### a. Scope Creep & Regulatory Creep

- Developers often tell contractors “just do what the City wants,” but cities don’t always give formal instructions.

- Contractor ends up eating delays and changes unless it’s clearly scoped in the bid and properly documented.

#### b. Payment Disputes

- The developer may delay payment, claiming the City hasn’t approved the work.

- Or they may wait until the City releases their performance security before paying the contractor—which could take months or years.

#### c. Design/Field Discrepancies

- Drawings approved by the City might not match actual site conditions.

- Contractor stuck between “built per drawing” and “City won’t approve unless it’s redone.”

#### d. No Payment Certifier

- Without a payment certifier (like on public jobs), it’s unclear who validates when work is completed or certifies substantial performance.

- This becomes critical for lien holdback timelines and substantial performance declarations under the Construction Act.

### 4. Construction Act Still Applies

Even though the project is private, the Construction Act rules still apply:

- 10% holdback until 45 days after substantial performance

- Lien rights (but not against the municipality if it’s their land—only against the developer’s interest)

- Prompt payment and adjudication if a proper invoice is issued

Watch Out: Developers sometimes claim that site servicing or infrastructure is outside the Construction Act (e.g., “it’s part of the municipal agreement”)—but that’s usually BS. Unless it’s 100% public land and 100% public money, the contractor likely has a lien right and should act accordingly.

### 5. Practical Strategies

- Clarify who the “owner” is under the Construction Act—it’s not always obvious

- Push for clear timelines in the servicing contract (especially for milestone approvals and payment triggers)

- Track and document all field directions, even if they come from the City via the developer

- Don’t wait too long to lien—even if the project seems “ongoing,” the 60/90 day clock can sneak up

- Ask for a copy of the site plan or servicing agreement—it helps map out what the City will or won’t allow

## Public Infrastructure: The Legal Landscape

infrastructure construction projects in Ontario, which usually means public sector work: municipal, provincial, or federally funded projects like roads, bridges, water systems, transit.

small to mid-sized infrastructure projects

### 1. Who’s Involved in Small Infra Jobs?

- Municipalities (cities, towns, townships)

- School boards or hospital authorities

- Crown corporations or agencies

- General contractors, often with a few key subs

- Consulting engineers and contract administrators (usually more influential than lawyers in early stages)

### 2. Procurement & Contracting

Smaller infrastructure jobs often use:

- RFT (Request for Tender) – fixed-price, low-bid wins

- RFP (Request for Proposals) – price + technical weighting

- Unit price contracts – for linear work like roads or watermains

- CCDC 4, 5A/5B or OPSS-based contracts – these are standardized, but municipalities often add brutal supplementary conditions.

Trap: Many municipalities bury aggressive clauses in their "Supplementary Conditions"—e.g., shifting design liability to the contractor, reducing claim timeframes, or limiting change order rights.

### 3. Construction Act Compliance

Yes, even small infrastructure projects are fully subject to:

- Prompt payment

- Adjudication

- Lien rights

But in infra jobs, you’re often dealing with:

- Municipal owners who can delay payment without consequences (in practice)

- Delays in certifying payment by the contract admin

- Subcontractors who aren’t looped in when payments are held

Proper Invoices must be submitted per the Act, and payment disputes go to adjudication, which can be useful—if the contractor is bold enough to trigger it.

### 4. Common Disputes

- Delay claims (especially utility conflicts, permit issues, site access)

- Unpaid extras / change orders

- Unforeseen site conditions (rock, contaminated soil, utilities not shown on drawings)

- Scope creep caused by poor design (and design consultants who gaslight the contractor)

- Aggressive contract administrators (often more interested in protecting the owner than being neutral)

Many small infra contractors don’t push back because:

- They want to stay on the bid list

- They can’t afford to adjudicate mid-project

- They don’t understand their legal rights under the Construction Act

### 5. Lien Rights on Public Lands

You can’t lien crown land, but here’s what you can do:

- File a Notice of Lien against the holdback held by the municipality or agency

- This protects your right to payment even if the project is on public land

- Must preserve lien within 60 days of last supply

- Must perfect within 90 days via court action

This is often misunderstood by subs and smaller GCs.

### 6. Strategic Tips for Contractors

- Read the Supplementary Conditions—they’re more important than the standard contract

- Document everything—diary notes, RFIs, site instructions, emails

- Submit delay notices in writing even if you think they’ll be ignored

- Watch the clock on invoicing, non-payment notices, lien and adjudication deadlines

- Build a relationship with the contract admin—they’re often the gatekeeper to payment

https://www.whitesandfirstnation.com/sagatay-economic-development

https://www.google.com/search?q=Sagatay+Economic+Development+whitesand+mining&sca_esv=8b3bacb7b59c53ad&rlz=1C5CHFA_enCA997CA997&ei=J4LcZ5i3K82z0PEPg6jtIA&start=10&sa=N&sstk=Af40H4XWomso2ancysekYaDTlEkdNKbnEcScXL0paubX7TebVFXnI-2Dwu_Yp8oUCNDwa5JKCExHsmMG38kKbSy_0JTM4SIo2Qqdlg&ved=2ahUKEwjY5omIx5mMAxXNGTQIHQNUGwQQ8NMDegQIGBAW&biw=2286&bih=1206&dpr=2

​​https://www.northwesthealthline.ca/displayservice.aspx?id=140598

https://www.ontario.ca/page/ministry-review-goldcorp-musselwhite-mine-main-power-supply-project-environmental-assessment