# TIER 1 LEAD MAGNET (CAMLO DIY COURSE FUNNEL)

# “FINTRAC MSB 24-Month Roadmap: The Essential Implementation Plan for New CAMLOs”

### A practical, immediately usable roadmap designed to build trust and accelerate confidence

## Purpose (Tier 1-Optimized)

- Give new CAMLOs, founders, and early-stage MSB operators a plug-and-play 24-month plan.

- Reduce confusion around what FINTRAC actually expects.

- Position your CAMLO Readiness Course as the natural next step to execute the roadmap.

This version intentionally emphasizes actionability, checklists, and low-friction DIY wins.

# Lead Magnet Structure (Tier 1 Version)

## Cover Page

FINTRAC MSB AML/ATF Roadmap (24 Months)
 A Practical, First-Year CAMLO Survival Framework

For new and expanding Canadian MSBs, payment firms, FX operators, and global remittance companies entering the Canadian marketplace.

# SECTION 1 — Why This Roadmap Exists

FINTRAC expects new MSBs to move from “registered” to “effective” extremely quickly.
 Most failures occur because operators don’t know:

- what sequence FINTRAC expects,

- what “effectiveness” looks like,

- and when key milestones must be met.

This roadmap provides your first 24 months of required AML/ATF program build-out, broken into simple, doable phases.

# SECTION 2 — Phase Breakdown

A visual breakdown of what must be completed and when, with simple bullet-based milestones.

## Phase 0 — Pre-Registration (Weeks 0–4)

Goal: Create the foundational AML/ATF structure needed for MSB registration.
 Your Checklist:

- CAMLO appointed (document authority + escalation paths).

- AML/ATF Program drafted (policies, risk assessment, training plan).

- Reporting & recordkeeping procedures outlined.

- Technology vendor decisions (KYC, screening, monitoring, data retention).

DIY Tip: FINTRAC expects coherence even if maturity is still in progress

## Phase 1 — Launch (Months 0–6)

Goal: Convert paperwork into real, functioning controls.
 Your Checklist:

- Deploy onboarding & KYC workflow.

- Implement sanctions, PEP, HIO screening.

- Configure transaction monitoring rules.

- Stand up a Compliance Committee.

- Begin basic testing (review samples monthly).

DIY Tip: “Operational, not theoretical” is a FINTRAC exam trigger phrase — aim for evidence.

## Phase 2 — Stabilization (Months 6–12)

Goal: Move from functioning to measurable effectiveness.
 Your Checklist:

- Conduct an internal effectiveness mini-review.

- Refresh risk assessment using real data.

- Tune alerting, reduce false positives.

- Provide first formal CAMLO report to board/CEO.

DIY Tip: Operators who delay tuning until Year 2 almost always fail exams.

## Phase 3 — Maturity Prep (Months 12–18)

Goal: Build defensible oversight and metrics.
 Your Checklist:

- Update P&Ps with real-world adjustments.

- Launch role-specific training.

- Track STR timeliness, onboarding rejection, EDD completion time, screening hit data.

- Conduct pre-audit testing.

DIY Tip: FINTRAC examiners heavily weight metrics; start tracking before Year 2.

## Phase 4 — Formal Two-Year Effectiveness Review (Months 18–24)

Goal: Complete the legally required independent review.
 Your Checklist:

- Independent end-to-end review.

- Full assessment of governance, training, KYC, screening, monitoring, reporting, recordkeeping.

- Management Action Plan (MAP) produced.

- Board approves MAP.

DIY Tip: FINTRAC will request this immediately in your first examination.

## Phase 5 — Post-Review Optimization (Month 24+)

Goal: Demonstrate continuous improvement to regulators.
 Your Checklist:

- Remediate all findings.

- Update P&Ps, training, and controls.

- Mature governance reporting cadence.

# SECTION 3 — Summary Table (Tier 1 Visual)

A clean one-page “cheat sheet” summarizing all phases, timeframes, and outputs.

# SECTION 4 — What New CAMLOs Usually Get Wrong

Designed to create demand for your DIY Course.

Common gaps:

- No coherent risk assessment until Year 2

- Controls are late to go live (months 4–9)

- No metrics

- No governance oversight evidence

- No pre-audit testing

- Policies not aligned to reality

This sets up the CTA.

# SECTION 5 — CTA: Next Step After the Roadmap

Download the CAMLO Readiness Course:
 A practical, self-paced course that helps MSB founders and new CAMLOs implement every phase in the roadmap with templates, walkthroughs, and FINTRAC-aligned tools.