# Agents

Pimps

Players

Dons

# Specific Case

# Specific Provisions

| - Risk of Payment Delays: | 29.1 If Subcontractor is delayed in the performance of the Subcontract Work by an action or omission of the Owner, Consultant or any other person or entity for whom the Owner or Consultant is responsible, (an “Owner Delay”) then Subcontractor shall only be entitled to payment, compensation or extension of time in relation to such Owner Delay if and when Contractor receives payment, compensation or extension of time from Owner and only to the extent such payment, compensation or extension of time is directly related to Subcontractor and the Subcontract Work. 29.6 Subcontractor shall not be entitled to any payment, compensation or extension of time unless Contractor receives a written Notice from Subcontractor within 24 hours of when the Subcontractor becomes aware of, or knows of, or ought reasonably to have known of, any situation that could potentially result in the commencement of a Delay.... |
| --- | --- |
| 2. Price Reductions in Agreed Price: | 15.4 If Contractor incurs any costs or damages arising from Subcontractor’s Defective Work, including due to performing all or part of the correction in accordance with Section 15.3, Subcontractor shall immediately and fully reimburse Contractor for all such costs and damages. Contractor shall be entitled to set off any such costs and damages from any payments owing to Subcontractor. ... 32.3 On the occurrence of any Subcontractor Event of Default not listed in Section 32.5 below, Contractor may give Subcontractor a Notice of Subcontractor Event of Default (a “Default Notice”). If such Subcontractor Event of Default shall continue for a period of 48 hours following such Default Notice, Contractor, without prejudice to any other rights or remedies it may have, may terminate this Subcontract, cure such Subcontractor Event of Default, make good any Defects or Defective Work, or may complete the outstanding Subcontract Work, all at the cost and expense of Subcontractor. |
| 3. Strict Change Order Procedures: | 27.4 Changes Involving the Owner (b) Subcontractor shall only be entitled to payment, compensation or extension of time in relation to an External Change if and when Owner approves such Change and Contractor receives payment, compensation or extension of time from the Owner. If such conditions are met, Subcontractor shall only be entitled to receive the portion of the payment, compensation and/or extension of time that relates specifically to the Subcontract Work and such payment, compensation and/or extension of time shall be recorded in a Change Order between Contractor and Subcontractor. |
| 4. Liquidated Damages; Pass-Through Liability | 34.1 If Subcontractor fails to comply with Contractor’s Schedule, and by reason thereof Contractor becomes liable for costs, damages or penalties, then Subcontractor shall pay to Contractor the proportion of such costs, damages or penalties that are related to Subcontractor's delay, or Contractor may deduct and set-off the same from the Subcontract Price. |
| Termination Rights: | 33.1 If the Prime Contract shall be terminated in whole or in part for any reason whatsoever, the Contractor may, by written notice to Subcontractor, terminate this Subcontract to the extent that performance is not required due to the entire or partial termination of the Prime Contract. Upon termination of this Subcontract, Subcontractor shall not be entitled to any payment or compensation except for payment for that portion of the Subcontract Work actually performed by Subcontractor and certified complete by the Consultant, except that Subcontractor shall only be entitled to such payment if and when Contractor receives such payment from Owner. 33.2 Contractor may suspend or terminate this Subcontract for convenience at any time upon ten (10) days’ Notice to Subcontractor. If this Subcontract is terminated under this Section 33.2, Subcontractor shall only be entitled to payment for that portion of the Subcontract Work actually performed by Subcontractor up to the termination date. All such Subcontract Work shall be certified complete by Consultant prior to Subcontractor becoming entitled to such payment. Subcontractor’s payment application for such payment shall comply with Schedule B, and shall be supported by reasonable and sufficient backup data substantiating Subcontractor’s right to payment. Under no circumstances shall Subcontractor be entitled to recover any Other Damages from Contractor as a result of any suspension or early termination. |

| Payment Delays: | general contractor payment delays pending approvals or the completion of certain milestones |
| --- | --- |
| Retention of Payment: | Excessive holdbacks or retainage provisions |
| Reductions in Agreed Price: | provisions permitting unilateral reductions in the agreed-upon price for services, often tied to alleged deficiencies or delays |
| Strict Change Order Procedures: | Formalistic and burdensome requirements for submitting and approving change orders |
| Invoice Requirements: | Excessively formal invoice requirements may impose stringent formatting and submission rules for invoices |
| Liquidated Damages | Unfair Liquidated Damages Provisions: |
| Pass-Through Liability | Pass-Through Liability provisions may make the subcontractor liable for delays, defects, or disputes caused by the general contractor, other subcontractors, or external factors. |
| Termination Rights: | The general contractor may reserve the right to terminate the agreement without cause |
| Insurance |  |
| Indemnity Obligations: | Overly broad indemnity provisions require the subcontractor to indemnify the general contractor for a wide range of claims |
| Dispute Resolution | Arbitration or dispute resolution clauses may favor the general contractor by requiring disputes to be resolved in forums or under rules that are costly or inaccessible. |